## 【ＥＮ】Ｒ7（上半期）事故発生一覧
List of accidents (Accidents that occurred in the first half of FY2025)
No | Date of occurrence |  | Time | Accident type | Accident category | Damage caused by the disaster | Construction type | Incident summary
1 | 2025-03-12 | Fri | 8:30 | Occupational hazard accidents | Flying / Falling | Injured 1 person (Total recovery: less than 3 months) | Others | At the spoil disposal site, after completing the cleaning of the catch basin during cleanup operations, workers were installing concrete covers on the catch basin. At that time, one of the two lifting hooks used for the sling came loose on the victim's side, causing the concrete cover to fall from a height of 15 cm onto the victim's right foot (not wearing safety shoes), resulting in injury (fracture of the distal phalanx of the right third toe). Furthermore, the contractor failed to immediately report the accident to the relevant authorities and the client as required. [The accident occurred in fiscal year 2024, but measures were implemented in fiscal year 2025.] | 残土処分場において、片付け作業の桝の清掃作業が完了したため、集水桝へコンクリート蓋を設置する作業を行っていたところ、２箇所の玉掛吊り金具のうち被害者側の金具が外れ、コンクリート蓋が高さ15cmから被災者右足（安全靴未着用）の上に落下し負傷（右第３趾末節骨骨折）したもの。 また、受注者は事故発生直後は直ちに関係機関及び発注者に報告する必要があるがその報告を怠っていた。【令和６年度に事故が発生したが、令和７年度に措置を行った】
2 | 2025-04-07 | Mon | 11:40 | Occupational hazard accidents | Falls / Slips | Injured 1 person (Total recovery: 6 months) | River construction | While dismantling the formwork for a sluice gate, the victim attempted to assist another worker who was not scheduled for that task. He climbed over the stopper at the edge of the work platform and moved outside the designated work passageway. The formwork panel he touched collapsed, causing him to fall from a height of 3.4 meters and sustain injuries. | 樋門の型枠解体作業中に、被害者が作業予定にない他の作業員の作業を手伝おうと、作業足場端部のストッパーを乗り越えて、決められた作業通路以外を移動したところ、手を掛けた型枠パネルが倒れ、３．４ｍの高さから転落し負傷したもの。
3 | 2025-05-13 | Tue | 13:10 | Public hazard accidents | Overhead line damage | Damage to the cable line | Road improvement construction | During drainage structure construction for road improvement construction, When the backhoe lifted and swung the free-gradient gutter, its arm contacted overhead wires (NTT) and the bundling hangers used to prevent wire detachment. The detachment of the bundling hangers caused the overhead wires (NTT) to lose support, causing them to sag approximately 1 meter. | 道路改良工事の排水構造物工施工において、自由勾配側溝据付に必要な側溝切断をするため、側溝を横倒しにする目的でバックホウで吊り上げて旋回したところ、アームが架空線（NTT）及び架空線脱落防止用の一束化用ハンガに接触し、一束化用ハンガが外れたことで、架空線(NTT)が支持を失い、1m程度垂れ下がったもの。
4 | 2025-05-17 | Sat | 2:40 | Public hazard accidents | Personal injury accident | Injured 1 person (Total recovery: less than 1 months) | Bridge reinforcement and repair construction | During bridge repair construction, while pedestrian walkways were restricted for the removal of expansion joints, a bicycle entered the work site. The cyclist fell over the uneven surface created by the removed expansion joint and sustained injuries. | 橋梁補修工事において、歩道を規制して伸縮装置の撤去作業を行っていたところ、現場内に自転車が進入し、撤去した伸縮装置部の段差で転倒し一般の方が負傷したもの。
5 | 2025-06-24 | Tue | 0:00 | Public hazard accidents | Facility damage | Damage to the pedestrian signal luminaire | C.C.BOX construction | While loading As shells onto a dump truck, a backhoe's boom struck and damaged a pedestrian signal luminaire fixture during a swing maneuver. | ダンプトラックにＡｓ殻を積み込んでいたバックホウが旋回した際に、ブームが歩行者用信号機灯具に接触し損傷したもの。
6 | 2025-07-01 | Tue | 15:30 | Public hazard accidents | Overhead line damage | Damage to the cable line | Road improvement construction | During preparatory construction for the test embankment, after completing the subgrade leveling, unauthorized grading work was performed, resulting in the backhoe boom severing one overhead line (telecommunications line, carrying 49 circuits). | 試験盛土の準備作業において、敷均し完了後、独断で整地作業を行い、バックホウのブームが架空線（通信線）１条（４９回線）を切断したもの。
7 | 2025-07-11 | Fri | 14:15 | Public hazard accidents | Overhead line damage | Damage to the cable line | pavement construction | During tidying-up operations, a curb was being lifted and rotated using a mobile crane (backhoe with crane, 0.45m³ class). The backhoe arm came into contact with an NTT messenger wire (H=5.8m) located overhead, severing the messenger wire. The resulting vibration caused a Chugoku Electric Power cable to become entangled. The messenger wire fell onto the roadway, striking two general vehicles traveling on the national highway and causing scrape damage to the vehicles. | 片付け作業として縁石を移動式クレーン（クレーン付きバックホウ0.45m3級）で揚重し旋回していたところ、上部にあったNTTメッセンジャーワイヤー（H=5.8m）にバックホウのアームが接触したためメッセンジャーワイヤーを切断するとともに、その振動で中国電力ケーブルの絡まりが発生。現道上にメッセンジャーワイヤーが落下し、国道を走行中の一般車両2台に接触し、車両に擦り傷の損傷が発生したもの。
8 | 2025-07-15 | Tue | 0:05 | Occupational hazard accidents | Traffic accident (road) | Damage to the chase vehicle (light truck) and 4-tonne tipper | Others | During tunnel warning system construction, while a 4-ton dump truck exited the alternating traffic lane following a signal from a traffic controller, the chase vehicle (a light truck) rear-ended the 4-ton dump truck. | トンネル警報設備工事において、片側交互規制内より交通誘導員の合図により規制内から４ｔダンプ車が退出した際、規制の追い上げ車（軽トラック）が４ｔダンプに追突したもの。
9 | 2025-07-22 | Tue | 9:20 | Public hazard accidents | Others | Damage to the bridge inspection vehicle (Rentaled) | Others | During bridge inspection operations, when the boom of the bridge inspection vehicle was activated, the cover at the tip of the third boom made contact with the main girder of the bridge. This resulted in damage to the cover at the boom tip and left contact marks on the main girder. | 橋梁点検業務において、橋梁点検車のブームを作動させた際に、第３ブーム先端のカバーが橋梁の主桁に接触し、ブーム先端のカバーに損傷が生じるとともに、主桁に接触跡が残ったもの。
(As of October 1, 2025) Excluding the Port and Airport Department